# ENVIRONMENTAL UNIT DELIVERABLES (revised 04/2014)

| DOCUMENT: | ASSIGNED TO: | DEADLINE/DELIVERED: | IC/UC APPROVAL: |
| --- | --- | --- | --- |
| Review the ICS 201, objectives and brief EU participants. Review Situation Displays. This is continuous each time the plan (ICS 201 or IAP) is updated. |  |  |  |
| Form 203 (Roles/Responsibilities of EU staff including Tech Specs) |  |  |  |
| Resources at Risk (environmental, cultural, economic) ICS 232 form [Prioritization for Day 1 and then Second Operational Period. Need to get this done prior to Tactics Meeting.] |  |  |  |
| Over flight assignments made, work with Air Ops to secure seating. 2 hour intervals or as necessary/safe. Over flight drawing/map after each flight. |  |  |  |
| Weather, MSDS for oil type, ADIOS for predicted fate/weathering, mass balance. |  |  |  |
| Work with OPS on Divisions and boundaries, display on OPS and Situation Maps |  |  |  |
| Trajectory (need for the entire next operational period for the Tactics meeting) |  |  |  |
| Contribute information to the ICS 209 form as requested by Planning Section Chief/Situation. Typically this is mass balance, shoreline impacts information. |  |  |  |
| Activate Oiled Wildlife Rescue, or put them on notice. Mobilize Wildlife Rehab/Requisition (if not done by OPS). |  |  |  |
| Waste Staging Area Equipment Requisition, Decontamination Area Requisition if requested by OPS. |  |  |  |
| Waste Survey Team Requisitioned, (documented on 215 during Tactics Mtg.). Waste tracking form developed. |  |  |  |
| List of necessary permits developed, progress to obtain and permit conditions tracked on spreadsheet. |  |  |  |
| SCAT Requisitioned, documented on 215 during Tactics Mtg.) |  |  |  |
| Cultural Resource Team – State Archeologist - notification/requisition. Assign to SCAT if appropriate. |  |  |  |
| Decontamination Plan for vessels not involved in the response (if requested by OPS) |  |  |  |
| # EU review of Salvage Plan (if applicable) |  |  |  |
| # Waste Management Plan (coordinate with OPS) |  |  |  |
| # SCAT Management Plan |  |  |  |
| Decant Permit (only if adequate storage is not available. Check with OPS or may be directed by UC) |  |  |  |
| Dispersant Decision Memo or General Message with justification (Go / No-Go / Evaluation). |  |  |  |
| In Situ Decision Memo or General Message with justification (Go / No-Go / Evaluation). |  |  |  |
| Gen Msg to PIO for Community RE: wildlife sightings and caution of haz materials |  |  |  |
| Oiled Wildlife Management Plan (if not staffed in OPS) |  |  |  |
| ESA or Historical Properties Consultations, if applicable (consultations will be done by federal agencies). May need language for permits or ICS 204s. |  |  |  |
| ICS 204 forms for IAP – EU message if applicable. |  |  |  |
| Submit Final Environmental Unit Log (Form 214) |  |  |  |
| Environmental Unit Summary (Form 224) for next Operational Period. |  |  |  |

*Acknowledgement is given to Tesoro for developing this form