## ICS233-CG_SimCell_2024 IES TTX
1. Incident Name: |  |  |  |  | INCIDENT OPEN ACTION TRACKER
ICS-233 (Rev 07-12)
2. No. | 3. Item | 4. For/POC | 5. Briefed POC (X) | 6. Start Date | 7. Status | 8. Target Date | 9. Actual Date
1 | Obtain SDS-Provide to ICP and Field Operations | SOFR
2 | Develop site safety plan | SOFR
3 | Prepare a Interested Parties communications plan & schedule community meeting. | LOFR
4 | Conduct Tribal consultation call | LOFR
5 | Contact local law enforcement and fire department to determine their need and ability to assist | LOFR
6 | Form a JIC and prepare a media plan, including Media briefing schedule and Media press conference | PIO
7 | Develop appropriate public safety advisory for release to news media | PIO
8 | Establish a robust social media program and media policy for responders on social media. Establish website. Identify need for language interpritation services. | PIO
9 | Establish site control (hot, warm, cold zones and security) | OSC/SOFR
10 | Establish staging areas | OSC/PSC
11 | Establish TRF, safety zone and notice to mariners for incident including NOTAM | OSC
12 | Establish appropriate division boundaries. | OSC/EUL
13 | Evaluate the need for night operations. | OSC
14 | Complete or confirm notifications | PSC
15 | Coordinate Plan Approval Process with UC | PSC
16 | Identify & quantify product on shore and water. | PSC
17 | Identify resources at risk | EUL
18 | Develop Waste Management Plan including detailed tracking of disposal | EUL
19 | Develop a SCAT Plan | EUL
20 | Provide Section 7 and 106 Consultation | EUL
21 | Develop community air monitoring plan. | EUL
22 | Develop inadvertant cultural resource discovery plan | EUL
23 | Identify potential for non-floating oil. | EUL
24 | Establish Documentation Plan | DOCL
25 | Establish ordering process and signature authority | LSC
26 | Develop a medical plan (coordinate with SOFR) | LSC
27 | Develop a communications plan | LSC
28 | Develop security plan | LSC
29 | Develop traffic plan | LSC
30 | Plan on round the clock meals for field and ICP 24/7 | LSC/FSC
31 | Establish claims number and process | FSC
32 | Have 'burn rate' for first day by Planning Meeting | FSC
33 | Establish spending authorization with spending limitations (delegation of authority for this response) | FSC
34 | Prepare for limited night operations | ALL